## Financials
Project Name | Month | PV | EV | AC
Apollo | Jun | 100000 | 95000 | 110000
Zeus | Jun | 75000 | 80000 | 72000
Hermes | Jun | 60000 | 58000 | 62000
Athena | Jun | 85000 | 78000 | 87000

## Timeline
Project Name | Start Date | End Date | Milestone | Status
Apollo | 2025-01-01 | 2025-06-30 | Design Complete | Green
Zeus | 2025-02-01 | 2025-07-15 | Testing Start | Yellow
Hermes | 2025-03-15 | 2025-08-01 | Go Live | Red
Athena | 2025-01-20 | 2025-06-15 | User Training | Green

## Resources
Resource Name | Skill | Allocation % | Project | PTO Dates
Amit | Dev | 100 | Apollo | 2025-07-05
Beena | Test | 80 | Zeus
Chirag | PM | 100 | Athena | 2025-08-10
Deepa | UX | 60 | Hermes

## Risks
Risk ID | Project | Description | Score | Impact | Mitigation
101 | Zeus | Vendor delay | 8 | High | Escalate vendor
102 | Apollo | Integration gaps | 6 | Medium | Add buffer
103 | Hermes | Security exposure | 9 | High | Security audit
104 | Athena | Client resistance | 7 | Medium | Client workshops

## RAID_Jira
Issue ID | Component | Description | Tag | Priority
RA123 | Backend | Recurring memory leak | Recurring | High
JI456 | UI | New accessibility bug | New | Medium
JI789 | API | API throttling | Recurring | High
RA987 | Deployment | Outage on release day | New | Critical

## Survey
Respondent Role | Change Sentiment | Comments
Manager | 3 | Too sudden, unclear roles
Developer | 2 | Don’t understand tool change
QA Lead | 5 | Excited to try new workflow
Analyst | 4 | Need more training before go-live